## DETAILS
#VALUE! | PROJECT 1 |  | PROJECT 2
PREPAYMENT CERTIFICATION DETAILS
Client Ministry | Special Committee On Rehabilitation of Public Schools |  | Lagos State Real Estate Regulatory Authority
Name of Project Supervisor | Engr. F.O Badejo |  | Engr. Osisami A. Bankole
Contractor name: | Messrs. Kinghorse International Limited |  | Messrs. FAB Investment Limited
Payment stage: | Final Payment |  | Final Payment
Project Description | Rehabilitation of Water Supply and Wastewater Facilities at Shasha Housing Estate, Shasha |  | Rehabilitation of Water Supply and Wastewater Facilities at Ibeshe Housing Estate
Local Gov. Area | Egbeda LCDA / Alimosho LGA |  | Ikorodu LGA
What is the Contract sum? | 88073488.21 |  | 64559134.32
What is the Revised Contract sum? | 205880977.45 |  | 208395819.68
Percentage of Advance payment? (as specified in the award letter) | 40% |  | 40%
What is the work completed to date? | 102940488.73 |  | 108940488.73
Is there 5% retention? | 5% |  | 5%
What is the Previous Payment? (if none, write Nil ) | Nil |  | Nil
Percentage of Advance payment refunded | 100% |  | 100%
Calculated Amount due (Do not edit) | 69898578.8315 |  | 85431820.3875
Write out Amount due in words | Sixty-Nine Million, Eight Hundred and Ninety-Eight Thousand, Five Hundred and Seventy-Eight Naira, Eighty-Three Kobo | (Sixty-Nine Million, Eight Hundred and Ninety-Eight Thousand, Five Hundred and Seventy-Eight Naira, Eighty-Three Kobo) | Sixty-Nine Million, Eighty Hundred and Ninety-Eight Thousand, Five Hundred and Seventy-Eight Naira, Eighty-Three Kobo | (Sixty-Nine Million, Eighty Hundred and Ninety-Eight Thousand, Five Hundred and Seventy-Eight Naira, Eighty-Three Kobo)
PROJECT DETAILS
Elements of work covered | construction of sedimentation tank, and the provision of pressure filter tank / treatment plant |  | construction of sedimentation tank, and the provision of pressure filter tank / treatment plant.
Statement of Project Objectives: | To provide water supply and wastewater facilities at Shasha Housing Estate, Shasha |  | To provide water supply and wastewater facilities at Shasha Housing Estate, Shasha
Date of Award | 31st August, 2021 |  | 31st August, 2021
Date of upward review | 30th October, 2024 |  | 30th October, 2024
Effective Date of Commencement: | - |  | -
Duration of Contract: | Four (4) Months |  | Four (4) Months
Date of Delivery (Store Only) | Nil |  | Nil
Date of Completion | Nil |  | Nil
Date of Inspection | 30th January, 2025 |  | 30th January, 2025
Percentage of Work done | 40%. |  | 40%.
Physical Stage of Work | Ongoing |  | Ongoing
Date of Report | 13th February, 2025
Is the scope specified in the BOQ OR BEME or Award letter ? | Bill of Quantities (BOQ).
FOLIO REFERENCES
Cover page | folio 1
Governor's Approval | folio 2 - 2d
Letter of award / upward review | folios 3 - 4
Prepayment certificate | folio 5
Inspection report | folio 6 - 7
Inspection report File number | MEPB/MED/25/162/I/6 |  | MEPB/MED/25/162/I/7
BOQ | folio 8
Valuation | N/A
Delivery notes | N/A
Project Brief | folio 9
APG | N/A
Valid Performance Bond | folios 10 - 10b
Letter of completion | N/A
Agency pictures | folios 11 - 11c
MED Pictures | folio 12
Checklist | folio 13
Folio reference for memo | Folios 1 - 13
Memo file number | MEPB/MED/25/162/I/14
Approval file number | MEPB/MED/25/162/I/15
ADDRESS LINE & DATE FOR APPROVAL
Approval date | 7th January, 2025
Address line 1 | The Special Adviser,
Address line 2 | Special Committee On Rehabilitation of Public Schools
Address line 3 | Block 21, The Secretariat.
Address line 4 | Alausa - Ikeja,
Address line 5 | Lagos.
Mail reference number | SAH/LASRERA/A.51/3B/145 |  | SAH/LASRERA/A.51/3B/145
Mail reference date | 14th January, 2025 |  | 14th January, 2025
SIGNATORIES
HOU/Staff 1 | Alawiye, K.T (Ms)
Designation | PPO (MED)
Staff 2 | Adekunle-Famuyon, F.A
Designation | PPO (MED)

## PC 1
Particulars of Contract: Final Payment | Final Payment
TOTAL CONTRACT SUM | 88073488.21
REVISED CONTRACT SUM | 205880977.45
ADVANCE PAYMENT | 35229395.284 |  | 40%
WORK COMPLETED TO DATE | 102940488.73
5% RETENTION | 5147024.4365 |  | 5%
TOTAL NET PAYMENT | 97793464.2935
7.5% VAT | 7334509.822
TOTAL NET AMOUNT | 105127974.1155
LESS ADVANCE PAYMENT REFUND | 35229395.284 |  | 100%
LESS PREVIOUS PAYMENT | Nil
AMOUNT DUE | 69898578.8315
| (Sixty-Nine Million, Eight Hundred and Ninety-Eight Thousand, Five Hundred and Seventy-Eight Naira, Eighty-Three Kobo) |  | ₦69,898,578.83
CUMMULATIVE | 105127974.1155
Certification of the sum of ₦69,898,578.83 (Sixty-Nine Million, Eight Hundred and Ninety-Eight Thousand, Five Hundred and Seventy-Eight Naira, Eighty-Three Kobo) only, in favour of Messrs. Kinghorse International Limited is recommended, please.
sum of ₦69,898,578.83 (Sixty-Nine Million, Eight Hundred and Ninety-Eight Thousand, Five Hundred and Seventy-Eight Naira, Eighty-Three Kobo) only, in favour of Messrs. Kinghorse International Limited is recommended, please.
sum of ₦69,898,578.83 (Sixty-Nine Million, Eight Hundred and Ninety-Eight Thousand, Five Hundred and Seventy-Eight Naira, Eighty-Three Kobo) only
Client Ministry | Special Committee On Rehabilitation of Public Schools
Name of Project Supervisor | Engr. F.O Badejo
Name of Contractor | Messrs. Kinghorse International Limited | MESSRS. KINGHORSE INTERNATIONAL LIMITED
Project Description | Rehabilitation of Water Supply and Wastewater Facilities at Shasha Housing Estate, Shasha
REHABILITATION OF WATER SUPPLY AND WASTEWATER FACILITIES AT SHASHA HOUSING ESTATE, SHASHA
Statement of Project Objectives: | To provide water supply and wastewater facilities at Shasha Housing Estate, Shasha
Local Gov. Area | Egbeda LCDA / Alimosho LGA
Date of Award | 31st August, 2021 | Date of upward review | 30th October, 2024
Effective Date of Commencement: | -
Expected Date of Completion | Four (4) Months
Duration of Contract: | Four (4) Months
Date of Delivery (Store Only) | Nil
Date of Completion | Nil
Date of Inspection | 30th January, 2025
Percentage of Work done | 40%.
Physical Stage of Work | Ongoing
Date of Report | 13th February, 2025
BOQ OR BEME | Bill of Quantities (BOQ).
Elements of work covered | construction of sedimentation tank, and the provision of pressure filter tank / treatment plant
Full Folio reference | Folios 1 - 13
Cover page | folio 1
Governor's Approval | folio 2 - 2d
Letter of award | folios 3 - 4
Prepayment certificate | folio 5
Inspection report | folio 6 - 7
BOQ | folio 8
Valuation | N/A
Delivery notes | N/A
Project Brief | folio 9
APG | N/A
Valid Performance Bond | folios 10 - 10b
Letter of completion | N/A
Agency pictures | folios 11 - 11c
MED Pictures | folio 12
Checklist | folio 13
Inspection report File number | MEPB/MED/25/162/I/6
Memo file number | MEPB/MED/25/162/I/14
Approval file number | MEPB/MED/25/162/I/15
Approval date | 7th January, 2025
Address line 1 | The Special Adviser,
Address line 2 | Special Committee On Rehabilitation of Public Schools
Address line 3 | Block 21, The Secretariat.
Address line 4 | Alausa - Ikeja,
Address line 5 | Lagos.
Mail reference number | SAH/LASRERA/A.51/3B/145
Mail reference date | 14th January, 2025
HOU (Sign) | Alawiye, K.T (Ms)
Designation | PPO (MED)
HOU member | Adekunle-Famuyon, F.A
Designation | PPO (MED)

## PC 2
Particulars of Contract: Final Payment | Final Payment
TOTAL CONTRACT SUM | 64559134.32
REVISED CONTRACT SUM | 208395819.68
ADVANCE PAYMENT | 25823653.728 |  | 40%
WORK COMPLETED TO DATE | 108940488.73
5% RETENTION | 5447024.4365 |  | 5%
TOTAL NET PAYMENT | 103493464.2935
7.5% VAT | 7762009.822
TOTAL NET AMOUNT | 111255474.1155
LESS ADVANCE PAYMENT REFUND | 25823653.728 |  | 100%
LESS PREVIOUS PAYMENT | Nil
AMOUNT DUE | 85431820.3875
| (Sixty-Nine Million, Eighty Hundred and Ninety-Eight Thousand, Five Hundred and Seventy-Eight Naira, Eighty-Three Kobo) |  | ₦85,431,820.39
CUMMULATIVE | 111255474.1155
Certification of the sum of ₦85,431,820.39 (Sixty-Nine Million, Eighty Hundred and Ninety-Eight Thousand, Five Hundred and Seventy-Eight Naira, Eighty-Three Kobo) only, in favour of Messrs. FAB Investment Limited is recommended, please.
sum of ₦85,431,820.39 (Sixty-Nine Million, Eighty Hundred and Ninety-Eight Thousand, Five Hundred and Seventy-Eight Naira, Eighty-Three Kobo) only, in favour of Messrs. FAB Investment Limited is recommended, please.
sum of ₦85,431,820.39 (Sixty-Nine Million, Eighty Hundred and Ninety-Eight Thousand, Five Hundred and Seventy-Eight Naira, Eighty-Three Kobo) only
Client Ministry | Lagos State Real Estate Regulatory Authority
Name of Project Supervisor | Engr. Osisami A. Bankole
Name of Contractor | Messrs. FAB Investment Limited | MESSRS. FAB INVESTMENT LIMITED
Project Description | Rehabilitation of Water Supply and Wastewater Facilities at Ibeshe Housing Estate
REHABILITATION OF WATER SUPPLY AND WASTEWATER FACILITIES AT IBESHE HOUSING ESTATE
Statement of Project Objectives: | To provide water supply and wastewater facilities at Shasha Housing Estate, Shasha
Local Gov. Area | Ikorodu LGA
Date of Award | 31st August, 2021 | Date of upward review | 30th October, 2024
Effective Date of Commencement: | -
Expected Date of Completion | Four (4) Months
Duration of Contract: | Four (4) Months
Date of Delivery (Store Only) | Nil
Date of Completion | Nil
Date of Inspection | 30th January, 2025
Percentage of Work done | 40%.
Physical Stage of Work | Ongoing
Date of Report | 0
BOQ OR BEME | 0
Elements of work covered | construction of sedimentation tank, and the provision of pressure filter tank / treatment plant.
Full Folio reference | 0
Cover page | 0
Governor's Approval | 0
Letter of award | 0
Prepayment certificate | 0
Inspection report | 0
BOQ | 0
Valuation | 0
Delivery notes | 0
Project Brief | 0
APG | 0
Valid Performance Bond | 0
Letter of completion | 0
Agency pictures | 0
MED Pictures | 0
Checklist | 0
Inspection report File number | MEPB/MED/25/162/I/7
Memo file number | 0
Approval file number | 0
Approval date | 0
Address line 1 | 0
Address line 2 | 0
Address line 3 | 0
Address line 4 | 0
Address line 5 | 0
Mail reference number | SAH/LASRERA/A.51/3B/145
Mail reference date | 14th January, 2025
HOU (Sign) | 0
Designation | 0
HOU member | 0
Designation | 0

## INSPECTION REPORT
MEPB/MED/25/162/I/6
LAGOS STATE GOVERNMENT
MINISTRY OF ECONOMIC PLANNING AND BUDGET
PRE-PAYMENT INSPECTION REPORT
Particulars of Contract: Final Payment
i. | Client Ministry | Special Committee On Rehabilitation of Public Schools
ii. | Name of Project Supervisor | Engr. F.O Badejo
iii. | Name of Contractor | Messrs. Kinghorse International Limited
iv. | Project Description | Rehabilitation of Water Supply and Wastewater Facilities at Shasha Housing Estate, Shasha
v. | Local Gov. Area | Egbeda LCDA / Alimosho LGA
vi. | Date of Award | 31st August, 2021
vii. | Date of Award (Upward Review) | 30th October, 2024
viii. | Expected Date of Completion | Four (4) Months
ix. | Date of Delivery (Store Only) | Nil
x. | Date of Completion | Nil
xi. | Date of Inspection | 30th January, 2025
xii. | Contract Sum | 88073488.21
xiii. | Revised Contract sum | 205880977.45
xiv. | Advance Payment | 35229395.284
xv. | Advance Payment Refund | 35229395.284
xvi. | Works Completed to Date | 102940488.73
xvii. | Percentage of Work done | 40%.
xviii. | Physical Stage of Work | Ongoing
xix. | Previous payment | Nil
xx. | Retention | 5147024.4365
xxi. | Payment Now Due | 69898578.8315
xxii. | VAT Included in Payment Certificate | Ye s ü No ☐
COMMENT [If No]
OBSERVATION (QUALITY OF WORK)
a. | Very Good
b. | Good
c. | fair
d. | poor
RECOMMENDATION
Certification of the sum of ₦69,898,578.83 (Sixty-Nine Million, Eight Hundred and Ninety-Eight Thousand, Five Hundred and Seventy-Eight Naira, Eighty-Three Kobo) only, in favour of Messrs. Kinghorse International Limited is recommended, please.
----------------------------------------- |  |  | -----------------------------------------
Mr. Oyede, Fouad Adepoju |  |  | Alawiye, K.T (Ms)
Director (Monitoring & Evaluation) |  |  | PPO (MED)
13th February, 2025
---------------------------------------- |  | ---------------------------------------- |  | ----------------------------------------
Mrs. Ojo Olayinka Modupe |  | Mr. Lekan Balogun |  | Mr. Ope George
Permanent Secretary |  | Special Adviser |  | Honourable Commissioner

## INSPECTION REPORT 2
MEPB/MED/25/162/I/7
LAGOS STATE GOVERNMENT
MINISTRY OF ECONOMIC PLANNING AND BUDGET
PRE-PAYMENT INSPECTION REPORT
Particulars of Contract: Final Payment
i. | Client Ministry | Lagos State Real Estate Regulatory Authority
ii. | Name of Project Supervisor | Engr. Osisami A. Bankole
iii. | Name of Contractor | Messrs. FAB Investment Limited
iv. | Project Description | Rehabilitation of Water Supply and Wastewater Facilities at Ibeshe Housing Estate
v. | Local Gov. Area | Ikorodu LGA
vi. | Date of Award | 31st August, 2021
vii. | Date of Award | 30th October, 2024
viii. | Expected Date of Completion | Four (4) Months
ix. | Date of Delivery (Store Only) | Nil
x. | Date of Completion | Nil
xi. | Date of Inspection | 30th January, 2025
xii. | Contract Sum | 64559134.32
xiii. | Revised Contract Sum | 208395819.68
xiv. | Advance Payment | 25823653.728
xv. | Advance Payment Refund | 25823653.728
xvi. | Works Completed to Date | 108940488.73
xvii. | Percentage of Work done | 40%.
xviii. | Physical Stage of Work | Ongoing
xix. | Previous payment | Nil
xx. | Retention | 5447024.4365
xxi. | Payment Now Due | 85431820.3875
xxii. | VAT Included in Payment Certificate | Ye s ü No ☐
COMMENT [If No]
OBSERVATION (QUALITY OF WORK)
a. | Very Good
b. | Good
c. | fair
d. | poor
RECOMMENDATION
Certification of the sum of ₦85,431,820.39 (Sixty-Nine Million, Eighty Hundred and Ninety-Eight Thousand, Five Hundred and Seventy-Eight Naira, Eighty-Three Kobo) only, in favour of Messrs. FAB Investment Limited is recommended, please.
----------------------------------------- |  |  | -----------------------------------------
Mr. Oyede, Fouad Adepoju |  |  | Alawiye, K.T (Ms)
Director (Monitoring & Evaluation) |  |  | PPO (MED)
13th February, 2025
---------------------------------------- |  | ---------------------------------------- |  | ----------------------------------------
Mrs. Ojo Olayinka Modupe |  | Mr. Lekan Balogun |  | Mr. Ope George
Permanent Secretary |  | Special Adviser |  | Honourable Commissioner

## CHECKLIST
MINISTRY OF ECONOMIC PLANNING & BUDGET
MONITORING AND EVALUATION DEPARTMENT (MED)
PROJECT MONITORING CHECKLIST
Project 1 Description: | Rehabilitation of Water Supply and Wastewater Facilities at Shasha Housing Estate, Shasha |  |  |  | Dated: | 13th February, 2025
Project 2 Description: | Rehabilitation of Water Supply and Wastewater Facilities at Ibeshe Housing Estate
Executing MDA(s): | Special Committee On Rehabilitation of Public Schools |  |  |  | Date of Award(s): | 31st August, 2021/31st August, 2021
Effective Date of Commencement: | - /- |  |  |  | Duration of Contract(s): | Four (4) Months/Four (4) Months
Name of Contractors: | Messrs. Kinghorse International Limited/Messrs. FAB Investment Limited |  |  |  | On Time (Yes/No): | Yes
Name of Representative from Executing MDAs: | Engr. F.O Badejo |  |  |  | Payment Status (Project 1&2): | Final Payment/Final Payment
Name of MED Team Lead: | Ms. Alawiye, K.T
1. Documents on File |  |  | Yes | No | Remarks
Executing MDAs Project Report Write-up |  |  | ü |  | See folio 9
Contract Award letters |  |  | ü |  | See folios 3 - 4
Pre-Payment Certificates |  |  | ü |  | See folio 5
Inspection Reports |  |  | ü |  | See folio 6 - 7
Bill of Quantities (BOQ). |  |  | ü |  | See folio 8
Advance Payment Guaranteed |  |  |  | ü | N/A
Valid Performance Bond |  |  |  | ü | See folios 10 - 10b
Delivery note(s) |  |  |  |  | N/A
Statement of Valuation from Executing MDAs |  |  |  | ü | See N/A
Is Percentage of work (Value) done greater than APG utilized? |  |  |  |  | See folio 6 - 7
Statement of Project Objectives: | To provide water supply and wastewater facilities at Shasha Housing Estate, Shasha/To provide water supply and wastewater facilities at Shasha Housing Estate, Shasha
2. Test Certificates, Warranties and Independent Certificates on File
Valid Test Certificate (CBR, Others Specify) |  |  |  |  | N/A
Manufacturers Test Results (Steels, Equipment, Others: Specify) |  |  |  |  | N/A
Product Warranties -1 |  |  |  |  | N/A
Certified Copy of Hydrographic/Bathymetric Survey |  |  |  |  | N/A
Other Certifications:
Executing Agency Pictures |  |  |  |  | See folios 11 - 11c
MED Pictures |  |  |  |  | See folio 12
3. Decision To Inspect Or Not
Satisfied with the Quality of Documentation |  |  | ü
If Not Satisfy Issues requiring attention:
4. Questions For Site Visit
Are site documentations sighted on site? |  |  | ü
Is the quality of work done satisfactory to the Stakeholders? |  |  | ü
5. Date of Site Visits: |  | Project 1: 30th January, 2025 / Project 2: 30th January, 2025
6. Overall Assessment of Work Done: |  | Project 1: 40%. (satisfactory) / Project 2: 40%. (satisfactory)
7. Recommended for Issuance of Certification of Payment: |  |  | ü
__________________ |  | ________________
Alawiye, K.T (Ms) |  | Adekunle-Famuyon, F.A
PPO (MED) |  | PPO (MED)
13th February, 2025

## MEMO
MEPB/MED/25/162/I/14
Permanent Secretary (MEPB),
Through:
Director (MED),
REPORT OF SITE INSPECTION ON THE REHABILITATION OF WATER SUPPLY AND WASTEWATER FACILITIES AT SHASHA HOUSING ESTATE, SHASHA AND REHABILITATION OF WATER SUPPLY AND WASTEWATER FACILITIES AT IBESHE HOUSING ESTATE
Folios 1 - 13 of file, refer please.
INTRODUCTION
2. The Special Committee On Rehabilitation of Public Schools forwarded Pre-Payment Certificate in respect of the above Projects. Elements of work covered in Project 1 includes construction of sedimentation tank, and the provision of pressure filter tank / treatment plant and Project 2 includes construction of sedimentation tank, and the provision of pressure filter tank / treatment plant.
3. The joint inspection to the Project site was carried out by the officers from the Monitoring and Evaluation Department of this Ministry (MEPB) along with the Project Officer from the Executing Agency to facilitate Payments due to the Contractor.
4. CONCLUSION
• The Projects had been Ongoing at the time of this inspection in line with the specification of the Bill of Quantities (BOQ).
• Please see folio 13 of file for relevant documents pages on MED Checklist.
5. RECOMMENDATION
Consequent upon this, kindly recommend to the Permanent Secretary (MEPB) to seek the approval of the Honorable Commissioner (MEPB) to certify the Original Pre-Payment Certificate and Inspection Report for the following amounts:
• Project 1: sum of ₦69,898,578.83 (Sixty-Nine Million, Eight Hundred and Ninety-Eight Thousand, Five Hundred and Seventy-Eight Naira, Eighty-Three Kobo) only in favour of Messrs. Kinghorse International Limited. This represents Final Payment due to the Contractor.
• Project 2: sum of ₦85,431,820.39 (Sixty-Nine Million, Eighty Hundred and Ninety-Eight Thousand, Five Hundred and Seventy-Eight Naira, Eighty-Three Kobo) only in favour of Messrs. FAB Investment Limited. This represents Final Payment due to the Contractor.
6. Submitted for further directives, please.
Alawiye, K.T (Ms) Adekunle-Famuyon, F.A
PPO (MED) PPO (MED)
13th February, 2025

## MED PICTURES (A)
MED PICTURES:
REHABILITATION OF WATER SUPPLY AND WASTEWATER FACILITIES AT SHASHA HOUSING ESTATE, SHASHA BY MESSRS. KINGHORSE INTERNATIONAL LIMITED

## MED PICTURES (B)
MED PICTURES:
REHABILITATION OF WATER SUPPLY AND WASTEWATER FACILITIES AT IBESHE HOUSING ESTATE BY MESSRS. FAB INVESTMENT LIMITED

## APPROVAL
MEPB/MED/25/162/I/15 7th January, 2025
The Special Adviser,
Special Committee On Rehabilitation of Public Schools
Block 21, The Secretariat.
Alausa - Ikeja,
Lagos.
PRE-PAYMENT CERTIFICATION:
REHABILITATION OF WATER SUPPLY AND WASTEWATER FACILITIES AT SHASHA HOUSING ESTATE, SHASHA & REHABILITATION OF WATER SUPPLY AND WASTEWATER FACILITIES AT IBESHE HOUSING ESTATE.
I am directed to refer to your letter Ref. No. SAH/LASRERA/A.51/3B/145 & SAH/LASRERA/A.51/3B/145 dated 14th January, 2025 & 14th January, 2025 respectively, on the above subject and inform you that approval for the Pre-payment Certificates has been granted in the following sums:
S/N | Contractor | Amount | Remarks
1 | Messrs. Kinghorse International Limited | 69898578.8315 | Final Payment
2 | Messrs. FAB Investment Limited | 85431820.3875 | Final Payment
2. The Original Inspection Report and Pre-Payment Certificate are attached for your information and further necessary actions, please.
3. Thank you.
Alawiye, K.T. (Ms.)
For: The Permanent Secretary

## APPROVAL (one reference)
MEPB/MED/25/162/I/15 7th January, 2025
The Special Adviser,
Special Committee On Rehabilitation of Public Schools
Block 21, The Secretariat.
Alausa - Ikeja,
Lagos.
PRE-PAYMENT CERTIFICATION:
REHABILITATION OF WATER SUPPLY AND WASTEWATER FACILITIES AT SHASHA HOUSING ESTATE, SHASHA & REHABILITATION OF WATER SUPPLY AND WASTEWATER FACILITIES AT IBESHE HOUSING ESTATE.
I am directed to refer to your letter Ref. No. SAH/LASRERA/A.51/3B/145 dated 14th January, 2025, on the above subject and inform you that approval for the Pre-payment Certificates has been granted in the following sums:
S/N | Contractor | Amount | Remarks
1 | Messrs. Kinghorse International Limited | 69898578.8315 | Final Payment
2 | Messrs. FAB Investment Limited | 85431820.3875 | Final Payment
2. The Original Inspection Report and Pre-Payment Certificate are attached for your information and further necessary actions, please.
3. Thank you.
Alawiye, K.T. (Ms.)
For: The Permanent Secretary