## DETAILS
#VALUE! | PROJECT 1 |  | PROJECT 2 |  | PROJECT 3
PREPAYMENT CERTIFICATION DETAILS
Client Ministry | Special Committee on Rehabilitation of Public Schools |  | Special Committee on Rehabilitation of Public Schools |  | Special Committee on Rehabilitation of Public Schools
Name of Project Supervisor | Engr. F.O Badejo |  | Engr. F.O Badejo |  | Engr. F.O Badejo
Contractor name: | Messrs. Aston Constructions Limited |  | Messrs. Kinghorse International Limited |  | Messrs. Andall Project Limited
Payment stage: | Retention Payment |  | Retention Payment |  | Final Payment
Project Description | Renovation of 17+1 Classroom Block A and Admin Block at Community Senior Grammar School, Ipaja, Ayobo LCDA, Alimosho |  | Renovation of 6 Classroom Block at African Church Primary Schools 2, Meiran |  | Renovation of 6 Classroom Block at Unity Senior College, Oke-Odo, Lagos
Local Gov. Area | Alimosho |  | Alimosho |  | Alimosho
What is the Contract sum? | 121451790.45 |  | 62818915.97 |  | 65487684.25
What is the Revised Contract sum? | 0 |  | 0 |  | 0
Percentage of Advance payment? (as specified in the award letter) | 0% |  | 0% |  | 70%
What is the work completed to date? | 112971918.46 |  | 57077219.48 |  | 58149740.78
Is there 5% retention? | 0% |  | 0% |  | 5%
What is the Previous Payment? (if none, write Nil ) | 115372571.73 |  | 59675597.77 |  | Nil
Percentage of Advance payment refunded | 100% |  | 100% |  | 100%
Calculated Amount due (Do no edit) | 6072240.6145 |  | 1682413.171 |  | 13544043.7966
Write out Amount due in words | Six Million, Seventy-Two Thousand, Two Hundred and Forty Naira, Sixty-One Kobo | (Six Million, Seventy-Two Thousand, Two Hundred and Forty Naira, Sixty-One Kobo) | One Million, Six Hundred and Eighty-Two Thousand, Four Hundred and Thirteen Naira, Seventeen Kobo | (One Million, Six Hundred and Eighty-Two Thousand, Four Hundred and Thirteen Naira, Seventeen Kobo) | Thirteen Million, Five Hundred and Fourteen-Four Thousand, Five Hundred and Forty-Three Naira, Eighty Kobo | (Thirteen Million, Five Hundred and Fourteen-Four Thousand, Five Hundred and Forty-Three Naira, Eighty Kobo)
PROJECT DETAILS
Elements of work covered | demolition/alteration works, substructure, concrete work, aluminium partitioning, roofing, doors, fittings and fixtures, windows, electrical installation, finishings, painting and decoration, external works among others |  | demolition/alteration works, substructure, concrete work, block work, roofing, doors, fittings and fixtures, windows, electrical installation, finishings, painting and decoration, external works among others |  | demolition/alteration works, substructure, concrete work, block work, roofing, doors, fittings and fixtures, windows, electrical installation, finishings, painting and decoration, external works among others
Statement of Project Objectives: | To enhance the learning environment and improve administrative efficiency. |  | To enhance the learning environment and improve administrative efficiency. |  | To enhance the learning environment and improve administrative efficiency.
Date of Award | 27th May, 2024 |  | 28th August, 2023 |  | 13th November, 2024.
Date of upward review | - |  | - |  | -
Effective Date of Commencement: | - |  | - |  | -
Duration of Contract: | Three (3) Months |  | Three (3) Months |  | Three (3) Months
Date of Delivery (Store Only) | Nil |  | Nil |  | Nil
Date of Completion | Nil |  | Nil |  | Nil
Date of Inspection | 2nd April, 2025 |  | 27th March, 2025 |  | 27th March, 2025
Percentage of Work done | 100%. |  | 100%. |  | 100%.
Physical Stage of Work | Completed |  | Completed |  | Completed
Date of Report | 17th April 2025
Is the scope specified in the BOQ OR BEME or Award letter ? | Bill of Quantities (BOQ).
FOLIO REFERENCES
Cover page | folios 1 - 2
Governor's Approval | N/A
Letter of award / upward review | folios 3 - 5a
Prepayment certificate | folios 6 - 8
Inspection report | folios 9 - 11
Inspection report File number | MEPB/MED/25/103/XI/9 |  | MEPB/MED/25/103/XI/10 |  | MEPB/MED/25/103/XI/11
BOQ | folios 12 - 12zv; folios 13 - 13p; & folios 14 - 14p;
Valuation | folios 15 - 15b; folios 16 - 16a; folios 17 - 17a
Delivery notes | N/A
Project Brief | folios 18 - 20
APG | N/A
Valid Performance Bond | N/A
Letter of completion | folios 21-22
Agency pictures | folios 23 - 23e; folios 24 - 24h; folios 25 - 25c
MED Pictures | folios 26 - 26a; folios 27 - 27a; folio 28
Checklist | folio 29
Folio reference for memo | Folios 1 - 29
Memo file number | MEPB/MED/25/103/XI/30
Approval file number | MEPB/MED/25/103/XI/31
ADDRESS LINE & DATE FOR APPROVAL
Approval date | 7th January, 2025
Address line 1 | The Chairman,
Address line 2 | Special Committee on Rehabilitation of Public Schools
Address line 3 | 16, Ogundana Street, Off Allen Avenue,
Address line 4 | Ikeja,
Address line 5 | Lagos.
Mail reference number | SCRPS/W/NS/006/2023/136 |  | SCRPS/W/NS/006/2023/136 |  | SCRPS/W/NS/006/2023/136
Mail reference date | 12th March, 2025 |  | 12th March, 2025 |  | 12th March, 2025
SIGNATORIES
HOU/Staff 1 | Alawiye, K.T (Ms)
Designation | PPO (MED)
Staff 2 | Adekunle-Famuyon, F.A
Designation | PPO (MED)

## PC 1
Particulars of Contract: Retention Payment | Retention Payment
TOTAL CONTRACT SUM | 121451790.45
REVISED CONTRACT SUM | 0
ADVANCE PAYMENT | 0 |  | 0%
WORK COMPLETED TO DATE | 112971918.46
5% RETENTION | 0 |  | 0%
TOTAL NET PAYMENT | 112971918.46
7.5% VAT | 8472893.8845
TOTAL NET AMOUNT | 121444812.3445
LESS ADVANCE PAYMENT REFUND | 0 |  | 100%
LESS PREVIOUS PAYMENT | 115372571.73
AMOUNT DUE | 6072240.6145
| (Six Million, Seventy-Two Thousand, Two Hundred and Forty Naira, Sixty-One Kobo) |  | ₦6,072,240.61
CUMMULATIVE | 121444812.3445
Certification of the sum of ₦6,072,240.61 (Six Million, Seventy-Two Thousand, Two Hundred and Forty Naira, Sixty-One Kobo) only, in favour of Messrs. Aston Constructions Limited is recommended, please.
sum of ₦6,072,240.61 (Six Million, Seventy-Two Thousand, Two Hundred and Forty Naira, Sixty-One Kobo) only, in favour of Messrs. Aston Constructions Limited is recommended, please.
sum of ₦6,072,240.61 (Six Million, Seventy-Two Thousand, Two Hundred and Forty Naira, Sixty-One Kobo) only
Client Ministry | Special Committee on Rehabilitation of Public Schools
Name of Project Supervisor | Engr. F.O Badejo
Name of Contractor | Messrs. Aston Constructions Limited | MESSRS. ASTON CONSTRUCTIONS LIMITED
Project Description | Renovation of 17+1 Classroom Block A and Admin Block at Community Senior Grammar School, Ipaja, Ayobo LCDA, Alimosho
RENOVATION OF 17+1 CLASSROOM BLOCK A AND ADMIN BLOCK AT COMMUNITY SENIOR GRAMMAR SCHOOL, IPAJA, AYOBO LCDA, ALIMOSHO
Statement of Project Objectives: | To enhance the learning environment and improve administrative efficiency.
Local Gov. Area | Alimosho
Date of Award | 27th May, 2024 | Date of upward review | -
Effective Date of Commencement: | -
Expected Date of Completion | Three (3) Months
Duration of Contract: | Three (3) Months
Date of Delivery (Store Only) | Nil
Date of Completion | Nil
Date of Inspection | 2nd April, 2025
Percentage of Work done | 100%.
Physical Stage of Work | Completed
Date of Report | 17th April 2025
BOQ OR BEME | Bill of Quantities (BOQ).
Elements of work covered | demolition/alteration works, substructure, concrete work, aluminium partitioning, roofing, doors, fittings and fixtures, windows, electrical installation, finishings, painting and decoration, external works among others
Full Folio reference | Folios 1 - 29
Cover page | folios 1 - 2
Governor's Approval | N/A
Letter of award | folios 3 - 5a
Prepayment certificate | folios 6 - 8
Inspection report | folios 9 - 11
BOQ | folios 12 - 12zv; folios 13 - 13p; & folios 14 - 14p;
Valuation | folios 15 - 15b; folios 16 - 16a; folios 17 - 17a
Delivery notes | N/A
Project Brief | folios 18 - 20
APG | N/A
Valid Performance Bond | N/A
Letter of completion | folios 21-22
Agency pictures | folios 23 - 23e; folios 24 - 24h; folios 25 - 25c
MED Pictures | folios 26 - 26a; folios 27 - 27a; folio 28
Checklist | folio 29
Inspection report File number | MEPB/MED/25/103/XI/9
Memo file number | MEPB/MED/25/103/XI/30
Approval file number | MEPB/MED/25/103/XI/31
Approval date | 7th January, 2025
Address line 1 | The Chairman,
Address line 2 | Special Committee on Rehabilitation of Public Schools
Address line 3 | 16, Ogundana Street, Off Allen Avenue,
Address line 4 | Ikeja,
Address line 5 | Lagos.
Mail reference number | SCRPS/W/NS/006/2023/136
Mail reference date | 12th March, 2025
HOU (Sign) | Alawiye, K.T (Ms)
Designation | PPO (MED)
HOU member | Adekunle-Famuyon, F.A
Designation | PPO (MED)

## PC 2
Particulars of Contract: Retention Payment | Retention Payment
TOTAL CONTRACT SUM | 62818915.97
REVISED CONTRACT SUM | 0
ADVANCE PAYMENT | 0 |  | 0%
WORK COMPLETED TO DATE | 57077219.48
5% RETENTION | 0 |  | 0%
TOTAL NET PAYMENT | 57077219.48
7.5% VAT | 4280791.461
TOTAL NET AMOUNT | 61358010.941
LESS ADVANCE PAYMENT REFUND | 0 |  | 100%
LESS PREVIOUS PAYMENT | 59675597.77
AMOUNT DUE | 1682413.171
| (One Million, Six Hundred and Eighty-Two Thousand, Four Hundred and Thirteen Naira, Seventeen Kobo) |  | ₦1,682,413.17
CUMMULATIVE | 61358010.941
Certification of the sum of ₦1,682,413.17 (One Million, Six Hundred and Eighty-Two Thousand, Four Hundred and Thirteen Naira, Seventeen Kobo) only, in favour of Messrs. Kinghorse International Limited is recommended, please.
sum of ₦1,682,413.17 (One Million, Six Hundred and Eighty-Two Thousand, Four Hundred and Thirteen Naira, Seventeen Kobo) only, in favour of Messrs. Kinghorse International Limited is recommended, please.
sum of ₦1,682,413.17 (One Million, Six Hundred and Eighty-Two Thousand, Four Hundred and Thirteen Naira, Seventeen Kobo) only
Client Ministry | Special Committee on Rehabilitation of Public Schools
Name of Project Supervisor | Engr. F.O Badejo
Name of Contractor | Messrs. Kinghorse International Limited | MESSRS. KINGHORSE INTERNATIONAL LIMITED
Project Description | Renovation of 6 Classroom Block at African Church Primary Schools 2, Meiran
RENOVATION OF 6 CLASSROOM BLOCK AT AFRICAN CHURCH PRIMARY SCHOOLS 2, MEIRAN
Statement of Project Objectives: | To enhance the learning environment and improve administrative efficiency.
Local Gov. Area | Alimosho
Date of Award | 28th August, 2023 | Date of upward review | -
Effective Date of Commencement: | -
Expected Date of Completion | Three (3) Months
Duration of Contract: | Three (3) Months
Date of Delivery (Store Only) | Nil
Date of Completion | Nil
Date of Inspection | 27th March, 2025
Percentage of Work done | 100%.
Physical Stage of Work | Completed
Date of Report | 0
BOQ OR BEME | 0
Elements of work covered | demolition/alteration works, substructure, concrete work, block work, roofing, doors, fittings and fixtures, windows, electrical installation, finishings, painting and decoration, external works among others
Full Folio reference | 0
Cover page | 0
Governor's Approval | 0
Letter of award | 0
Prepayment certificate | 0
Inspection report | 0
BOQ | 0
Valuation | 0
Delivery notes | 0
Project Brief | 0
APG | 0
Valid Performance Bond | 0
Letter of completion | 0
Agency pictures | 0
MED Pictures | 0
Checklist | 0
Inspection report File number | MEPB/MED/25/103/XI/10
Memo file number | 0
Approval file number | 0
Approval date | 0
Address line 1 | 0
Address line 2 | 0
Address line 3 | 0
Address line 4 | 0
Address line 5 | 0
Mail reference number | SCRPS/W/NS/006/2023/136
Mail reference date | 12th March, 2025
HOU (Sign) | 0
Designation | 0
HOU member | 0
Designation | 0

## PC 3
Particulars of Contract: Final Payment | Final Payment
TOTAL CONTRACT SUM | 65487684.25
REVISED CONTRACT SUM | 0
ADVANCE PAYMENT | 45841378.975 |  | 70%
WORK COMPLETED TO DATE | 58149740.78
5% RETENTION | 2907487.039 |  | 5%
TOTAL NET PAYMENT | 55242253.741
7.5% VAT | 4143169.0306
TOTAL NET AMOUNT | 59385422.7716
LESS ADVANCE PAYMENT REFUND | 45841378.975 |  | 100%
LESS PREVIOUS PAYMENT | Nil
AMOUNT DUE | 13544043.7966
| (Thirteen Million, Five Hundred and Fourteen-Four Thousand, Five Hundred and Forty-Three Naira, Eighty Kobo) |  | ₦13,544,043.80
CUMMULATIVE | 59385422.7716
Certification of the sum of ₦13,544,043.80 (Thirteen Million, Five Hundred and Fourteen-Four Thousand, Five Hundred and Forty-Three Naira, Eighty Kobo) only, in favour of Messrs. Andall Project Limited is recommended, please.
sum of ₦13,544,043.80 (Thirteen Million, Five Hundred and Fourteen-Four Thousand, Five Hundred and Forty-Three Naira, Eighty Kobo) only, in favour of Messrs. Andall Project Limited is recommended, please.
sum of ₦13,544,043.80 (Thirteen Million, Five Hundred and Fourteen-Four Thousand, Five Hundred and Forty-Three Naira, Eighty Kobo) only
Client Ministry | Special Committee on Rehabilitation of Public Schools
Name of Project Supervisor | Engr. F.O Badejo
Name of Contractor | Messrs. Andall Project Limited | MESSRS. ANDALL PROJECT LIMITED
Project Description | Renovation of 6 Classroom Block at Unity Senior College, Oke-Odo, Lagos
RENOVATION OF 6 CLASSROOM BLOCK AT UNITY SENIOR COLLEGE, OKE-ODO, LAGOS
Statement of Project Objectives: | To enhance the learning environment and improve administrative efficiency.
Local Gov. Area | Alimosho
Date of Award | 28th August, 2023 | Date of upward review | -
Effective Date of Commencement: | -
Expected Date of Completion | Three (3) Months
Duration of Contract: | Three (3) Months
Date of Delivery (Store Only) | Nil
Date of Completion | Nil
Date of Inspection | 27th March, 2025
Percentage of Work done | 100%.
Physical Stage of Work | Completed
Date of Report | 0
BOQ OR BEME | 0
Elements of work covered | demolition/alteration works, substructure, concrete work, block work, roofing, doors, fittings and fixtures, windows, electrical installation, finishings, painting and decoration, external works among others
Full Folio reference | 0
Cover page | 0
Governor's Approval | 0
Letter of award | 0
Prepayment certificate | 0
Inspection report | 0
BOQ | 0
Valuation | 0
Delivery notes | 0
Project Brief | 0
APG | 0
Valid Performance Bond | 0
Letter of completion | 0
Agency pictures | 0
MED Pictures | 0
Checklist | 0
Inspection report File number | MEPB/MED/25/103/XI/11
Memo file number | 0
Approval file number | 0
Approval date | 0
Address line 1 | 0
Address line 2 | 0
Address line 3 | 0
Address line 4 | 0
Address line 5 | 0
Mail reference number | SCRPS/W/NS/006/2023/136
Mail reference date | 12th March, 2025
HOU (Sign) | 0
Designation | 0
HOU member | 0
Designation | 0

## INSPECTION REPORT
MEPB/MED/25/103/XI/9
LAGOS STATE GOVERNMENT
MINISTRY OF ECONOMIC PLANNING AND BUDGET
PRE-PAYMENT INSPECTION REPORT
Particulars of Contract: Retention Payment
i. | Client Ministry | Special Committee on Rehabilitation of Public Schools
ii. | Name of Project Supervisor | Engr. F.O Badejo
iii. | Name of Contractor | Messrs. Aston Constructions Limited
iv. | Project Description | Renovation of 17+1 Classroom Block A and Admin Block at Community Senior Grammar School, Ipaja, Ayobo LCDA, Alimosho
v. | Local Gov. Area | Alimosho
vi. | Date of Award | 27th May, 2024
vii. | Date of Award (Upward Review) | -
viii. | Expected Date of Completion | Three (3) Months
ix. | Date of Delivery (Store Only) | Nil
x. | Date of Completion | Nil
xi. | Date of Inspection | 2nd April, 2025
xii. | Contract Sum | 121451790.45
xiii. | Revised Contract sum | 0
xiv. | Advance Payment | 0
xv. | Advance Payment Refund | 0
xvi. | Works Completed to Date | 112971918.46
xvii. | Percentage of Work done | 100%.
xviii. | Physical Stage of Work | Completed
xix. | Previous payment | 115372571.73
xx. | Retention | 0
xxi. | Payment Now Due | 6072240.6145
xxii. | VAT Included in Payment Certificate | Ye s ü No ☐
COMMENT [If No]
OBSERVATION (QUALITY OF WORK)
a. | Very Good
b. | Good
c. | fair
d. | poor
RECOMMENDATION
Certification of the sum of ₦6,072,240.61 (Six Million, Seventy-Two Thousand, Two Hundred and Forty Naira, Sixty-One Kobo) only, in favour of Messrs. Aston Constructions Limited is recommended, please.
----------------------------------------- |  |  | -----------------------------------------
Mr. Oyede, Fouad Adepoju |  |  | Alawiye, K.T (Ms)
Director (Monitoring & Evaluation) |  |  | PPO (MED)
17th April 2025
---------------------------------------- |  | ---------------------------------------- |  | ----------------------------------------
Mrs. Ojo Olayinka Modupe |  | Mr. Lekan Balogun |  | Mr. Ope George
Permanent Secretary |  | Special Adviser |  | Honourable Commissioner

## INSPECTION REPORT 2
MEPB/MED/25/103/XI/10
LAGOS STATE GOVERNMENT
MINISTRY OF ECONOMIC PLANNING AND BUDGET
PRE-PAYMENT INSPECTION REPORT
Particulars of Contract: Retention Payment
i. | Client Ministry | Special Committee on Rehabilitation of Public Schools
ii. | Name of Project Supervisor | Engr. F.O Badejo
iii. | Name of Contractor | Messrs. Kinghorse International Limited
iv. | Project Description | Renovation of 6 Classroom Block at African Church Primary Schools 2, Meiran
v. | Local Gov. Area | Alimosho
vi. | Date of Award | 28th August, 2023
vii. | Date of Award | -
viii. | Expected Date of Completion | Three (3) Months
ix. | Date of Delivery (Store Only) | Nil
x. | Date of Completion | Nil
xi. | Date of Inspection | 27th March, 2025
xii. | Contract Sum | 62818915.97
xiii. | Revised Contract Sum | 0
xiv. | Advance Payment | 0
xv. | Advance Payment Refund | 0
xvi. | Works Completed to Date | 57077219.48
xvii. | Percentage of Work done | 100%.
xviii. | Physical Stage of Work | Completed
xix. | Previous payment | 59675597.77
xx. | Retention | 0
xxi. | Payment Now Due | 1682413.171
xxii. | VAT Included in Payment Certificate | Ye s ü No ☐
COMMENT [If No]
OBSERVATION (QUALITY OF WORK)
a. | Very Good
b. | Good
c. | fair
d. | poor
RECOMMENDATION
Certification of the sum of ₦1,682,413.17 (One Million, Six Hundred and Eighty-Two Thousand, Four Hundred and Thirteen Naira, Seventeen Kobo) only, in favour of Messrs. Kinghorse International Limited is recommended, please.
----------------------------------------- |  |  | -----------------------------------------
Mr. Oyede, Fouad Adepoju |  |  | Alawiye, K.T (Ms)
Director (Monitoring & Evaluation) |  |  | PPO (MED)
17th April 2025
---------------------------------------- |  | ---------------------------------------- |  | ----------------------------------------
Mrs. Ojo Olayinka Modupe |  | Mr. Lekan Balogun |  | Mr. Ope George
Permanent Secretary |  | Special Adviser |  | Honourable Commissioner

## INSPECTION REPORT 3
MEPB/MED/25/103/XI/11
LAGOS STATE GOVERNMENT
MINISTRY OF ECONOMIC PLANNING AND BUDGET
PRE-PAYMENT INSPECTION REPORT
Particulars of Contract: Final Payment
i. | Client Ministry | Special Committee on Rehabilitation of Public Schools
ii. | Name of Project Supervisor | Engr. F.O Badejo
iii. | Name of Contractor | Messrs. Andall Project Limited
iv. | Project Description | Renovation of 6 Classroom Block at Unity Senior College, Oke-Odo, Lagos
v. | Local Gov. Area | Alimosho
vi. | Date of Award | 28th August, 2023
vii. | Date of Award | -
viii. | Expected Date of Completion | Three (3) Months
ix. | Date of Delivery (Store Only) | Nil
x. | Date of Completion | Nil
xi. | Date of Inspection | 27th March, 2025
xii. | Contract Sum | 65487684.25
xiii. | Revised Contract Sum | 0
xiv. | Advance Payment | 45841378.975
xv. | Advance Payment Refund | 45841378.975
xvi. | Works Completed to Date | 58149740.78
xvii. | Percentage of Work done | 100%.
xviii. | Physical Stage of Work | Completed
xix. | Previous payment | Nil
xx. | Retention | 2907487.039
xxi. | Payment Now Due | 13544043.7966
xxii. | VAT Included in Payment Certificate | Ye s ü No ☐
COMMENT [If No]
OBSERVATION (QUALITY OF WORK)
a. | Very Good
b. | Good
c. | fair
d. | poor
RECOMMENDATION
Certification of the sum of ₦13,544,043.80 (Thirteen Million, Five Hundred and Fourteen-Four Thousand, Five Hundred and Forty-Three Naira, Eighty Kobo) only, in favour of Messrs. Andall Project Limited is recommended, please.
----------------------------------------- |  |  | -----------------------------------------
Mr. Oyede, Fouad Adepoju |  |  | Alawiye, K.T (Ms)
Director (Monitoring & Evaluation) |  |  | PPO (MED)
17th April 2025
---------------------------------------- |  | ---------------------------------------- |  | ----------------------------------------
Mrs. Ojo Olayinka Modupe |  | Mr. Lekan Balogun |  | Mr. Ope George
Permanent Secretary |  | Special Adviser |  | Honourable Commissioner

## CHECKLIST
MINISTRY OF ECONOMIC PLANNING & BUDGET
MONITORING AND EVALUATION DEPARTMENT (MED)
PROJECT MONITORING CHECKLIST
Project 1 Description: | Renovation of 17+1 Classroom Block A and Admin Block at Community Senior Grammar School, Ipaja, Ayobo LCDA, Alimosho |  |  |  | Dated: | 17th April 2025
Project 2 Description: | Renovation of 6 Classroom Block at African Church Primary Schools 2, Meiran
Project 3 Description: | Renovation of 6 Classroom Block at Unity Senior College, Oke-Odo, Lagos
Executing MDA(s): | Special Committee on Rehabilitation of Public Schools |  |  |  | Date of Award(s): | 27th May, 2024/28th August, 2023/28th August, 2023
Effective Date of Commencement: | - /- |  |  |  | Duration of Contract(s): | Three (3) Months/Three (3) Months/Three (3) Months
Name of Contractor: | Messrs. Aston Constructions Limited/Messrs. Kinghorse International Limited/Messrs. Andall Project Limited |  |  |  | On Time (Yes/No): | Yes
Name of Representative from Executing MDAs: | Engr. F.O Badejo |  |  |  | Payment Status (Project 1-3): | Retention Payment/Retention Payment/Final Payment
Name of MED Team Lead: | Ms. Alawiye, K.T
1. Documents on File |  |  | Yes | No | Remarks
Executing MDAs Project Report Write-up |  |  | ü |  | See folios 18 - 20
Contract Award letters |  |  | ü |  | See folios 3 - 5a
Pre-Payment Certificates |  |  | ü |  | See folios 6 - 8
Inspection Reports |  |  | ü |  | See folios 9 - 11
Bill of Quantities (BOQ). |  |  | ü |  | See folios 12 - 12zv; folios 13 - 13p; & folios 14 - 14p;
Advance Payment Guaranteed |  |  |  | ü | N/A
Valid Performance Bond |  |  |  | ü | N/A
Delivery note(s) |  |  |  |  | N/A
Statement of Valuation from Executing MDAs |  |  |  | ü | See folios 15 - 15b; folios 16 - 16a; folios 17 - 17a
Is Percentage of work (Value) done greater than APG utilized? |  |  |  |  | See folios 9 - 11
Statement of Project Objectives: | To enhance the learning environment and improve administrative efficiency.
2. Test Certificates, Warranties and Independent Certificates on File
Valid Test Certificate (CBR, Others Specify) |  |  |  |  | N/A
Manufacturers Test Results (Steels, Equipment, Others: Specify) |  |  |  |  | N/A
Product Warranties -1 |  |  |  |  | N/A
Certified Copy of Hydrographic/Bathymetric Survey |  |  |  |  | N/A
Other Certifications:
Executing Agency Pictures |  |  |  |  | See folios 23 - 23e; folios 24 - 24h; folios 25 - 25c
MED Pictures |  |  |  |  | See folios 26 - 26a; folios 27 - 27a; folio 28
3. Decision To Inspect Or Not
Satisfied with the Quality of Documentation |  |  | ü
If Not Satisfy Issues requiring attention:
4. Questions For Site Visit
Are site documentations sighted on site? |  |  | ü
Is the quality of work done satisfactory to the Stakeholders? |  |  | ü
5. Date of Site Visits: |  | Project 1: 2nd April, 2025 / Project 2: 27th March, 2025 / Project 3: 27th March, 2025
6. Overall Assessment of Work Done: |  | Project 1: 100%. (satisfactory) / Project 2: 100%. (satisfactory) / Project 3: 100%. (satisfactory)
7. Recommended for Issuance of Certification of Payment: |  |  | ü
__________________ |  | ________________
Alawiye, K.T (Ms) |  | Adekunle-Famuyon, F.A
PPO (MED) |  | PPO (MED)
17th April 2025

## MEMO
MEPB/MED/25/103/XI/30
Permanent Secretary (MEPB),
Through:
Director (MED),
REPORT OF SITE INSPECTION ON THE RENOVATION OF 17+1 CLASSROOM BLOCK A AND ADMIN BLOCK AT COMMUNITY SENIOR GRAMMAR SCHOOL, IPAJA, AYOBO LCDA, ALIMOSHO, RENOVATION OF 6 CLASSROOM BLOCK AT AFRICAN CHURCH PRIMARY SCHOOLS 2, MEIRAN AND RENOVATION OF 6 CLASSROOM BLOCK AT UNITY SENIOR COLLEGE, OKE-ODO, LAGOS.
Folios 1 - 29 of file, refer please.
INTRODUCTION
2. The Special Committee on Rehabilitation of Public Schools forwarded Pre-Payment Certificate in respect of the above Projects. Elements of work covered in Project 1 includes demolition/alteration works, substructure, concrete work, aluminium partitioning, roofing, doors, fittings and fixtures, windows, electrical installation, finishings, painting and decoration, external works among others. Project 2 includes demolition/alteration works, substructure, concrete work, block work, roofing, doors, fittings and fixtures, windows, electrical installation, finishings, painting and decoration, external works among others. Project 3 includes demolition/alteration works, substructure, concrete work, block work, roofing, doors, fittings and fixtures, windows, electrical installation, finishings, painting and decoration, external works among others
3. The joint inspection to the Project site was carried out by the officers from the Monitoring and Evaluation Department of this Ministry (MEPB) along with the Project Officer from the Executing Agency to facilitate Payments due to the Contractor.
4. CONCLUSION
• The Projects had been Completed at the time of this inspection in line with the specification of the Bill of Quantities (BOQ).
• The 6(six) months defect liability period of Projects 2 & 3 had elapsed. Kindly refer to folios 21-22 for certificate of final completion.
• Please see folio 29 of file for relevant documents pages on MED Checklist.
5. RECOMMENDATION
Consequent upon this, kindly recommend to the Permanent Secretary (MEPB) to seek the approval of the Honorable Commissioner (MEPB) to certify the Original Pre-Payment Certificate and Inspection Report for the following amounts:
• Project 1: sum of ₦6,072,240.61 (Six Million, Seventy-Two Thousand, Two Hundred and Forty Naira, Sixty-One Kobo) only in favour of Messrs. Aston Constructions Limited. This represents Retention Payment due to the Contractor.
• Project 2: sum of ₦1,682,413.17 (One Million, Six Hundred and Eighty-Two Thousand, Four Hundred and Thirteen Naira, Seventeen Kobo) only in favour of Messrs. Kinghorse International Limited. This represents Retention Payment due to the Contractor.
• Project 3: sum of ₦13,544,043.80 (Thirteen Million, Five Hundred and Fourteen-Four Thousand, Five Hundred and Forty-Three Naira, Eighty Kobo) only in favour of Messrs. Andall Project Limited. This represents Final Payment due to the Contractor.
6. Submitted for further directives, please.
Alawiye, K.T (Ms) Adekunle-Famuyon, F.A
PPO (MED) PPO (MED)
17th April 2025

## MEMO (2)
MEPB/MED/25/103/XI/30
Permanent Secretary (MEPB),
Through:
Director (MED),
REPORT OF SITE INSPECTION ON THE RENOVATION OF 17+1 CLASSROOM BLOCK A AND ADMIN BLOCK AT COMMUNITY SENIOR GRAMMAR SCHOOL, IPAJA, AYOBO LCDA, ALIMOSHO, RENOVATION OF 6 CLASSROOM BLOCK AT AFRICAN CHURCH PRIMARY SCHOOLS 2, MEIRAN AND RENOVATION OF 6 CLASSROOM BLOCK AT UNITY SENIOR COLLEGE, OKE-ODO, LAGOS.
Folios 1 - 29 of file, refer please.
INTRODUCTION
The Special Committee on Rehabilitation of Public Schools has forwarded the Pre‑Payment Certificate for the above projects. All three projects include demolition and alteration works, substructure, concrete works, roofing, doors, fittings and fixtures, windows, electrical installations, finishes, painting and decoration, and external works; Project 1 additionally covers aluminium partitioning, while Projects 2 and 3 also involve block work.
3. The joint inspection to the Project site was carried out by the officers from the Monitoring and Evaluation Department of this Ministry (MEPB) along with the Project Officer from the Executing Agency to facilitate Payments due to the Contractor.
4. CONCLUSION
• The Projects had been Completed at the time of this inspection in line with the specification of the Bill of Quantities (BOQ).
• The 6(six) months defect liability period of Projects 2 & 3 had elapsed. Kindly refer to folios 21-22 for certificate of final completion.
• Please see folio 29 of file for relevant documents pages on MED Checklist.
5. RECOMMENDATION
Consequent upon this, kindly recommend to the Permanent Secretary (MEPB) to seek the approval of the Honorable Commissioner (MEPB) to certify the Original Pre-Payment Certificate and Inspection Report for the following amounts:
• Project 1: sum of ₦6,072,240.61 (Six Million, Seventy-Two Thousand, Two Hundred and Forty Naira, Sixty-One Kobo) only in favour of Messrs. Aston Constructions Limited. This represents Retention payment due to the Contractor.
• Project 2: sum of ₦1,682,413.17 (One Million, Six Hundred and Eighty-Two Thousand, Four Hundred and Thirteen Naira, Seventeen Kobo) only in favour of Messrs. Kinghorse International Limited. This represents Retention payment due to the Contractor.
• Project 3: sum of ₦13,544,043.80 (Thirteen Million, Five Hundred and Fourteen-Four Thousand, Five Hundred and Forty-Three Naira, Eighty Kobo) only in favour of Name of Contractor. This represents Retention payment due to the Contractor.
6. Submitted for further directives, please.
Alawiye, K.T (Ms) Adekunle-Famuyon, F.A
PPO (MED) PPO (MED)
17th April 2025

## MED PICTURES (A)
MED PICTURES:
RENOVATION OF 17+1 CLASSROOM BLOCK A AND ADMIN BLOCK AT COMMUNITY SENIOR GRAMMAR SCHOOL, IPAJA, AYOBO LCDA, ALIMOSHO BY MESSRS. ASTON CONSTRUCTIONS LIMITED

## MED PICTURES (B)
MED PICTURES:
RENOVATION OF 6 CLASSROOM BLOCK AT AFRICAN CHURCH PRIMARY SCHOOLS 2, MEIRAN BY MESSRS. KINGHORSE INTERNATIONAL LIMITED

## MED PICTURES (C)
MED PICTURES:
RENOVATION OF 6 CLASSROOM BLOCK AT UNITY SENIOR COLLEGE, OKE-ODO, LAGOS BY MESSRS. ANDALL PROJECT LIMITED

## APPROVAL
MEPB/MED/25/103/XI/31 7th January, 2025
The Chairman,
Special Committee on Rehabilitation of Public Schools
16, Ogundana Street, Off Allen Avenue,
Ikeja,
Lagos.
PRE-PAYMENT CERTIFICATION:
RENOVATION OF 17+1 CLASSROOM BLOCK A AND ADMIN BLOCK AT COMMUNITY SENIOR GRAMMAR SCHOOL, IPAJA, AYOBO LCDA, ALIMOSHO & RENOVATION OF 6 CLASSROOM BLOCK AT AFRICAN CHURCH PRIMARY SCHOOLS 2, MEIRAN & RENOVATION OF 6 CLASSROOM BLOCK AT UNITY SENIOR COLLEGE, OKE-ODO, LAGOS
I am directed to refer to your letter Ref. No. SCRPS/W/NS/006/2023/136 & SCRPS/W/NS/006/2023/136 & SCRPS/W/NS/006/2023/136 dated 12th March, 2025 & 12th March, 2025 & 12th March, 2025 respectively, on the above subject and inform you that approval for the Pre-payment Certificates has been granted in the following sums:
S/N | Contractor | Amount | Remarks
1 | Messrs. Aston Constructions Limited | 6072240.6145 | Retention Payment
2 | Messrs. Kinghorse International Limited | 1682413.171 | Retention Payment
3 | Messrs. Andall Project Limited | 13544043.7966 | Final Payment
2. The Original Inspection Report and Pre-Payment Certificate are attached for your information and further necessary actions, please.
3. Thank you.
Alawiye, K.T. (Ms.)
For: The Permanent Secretary

## APPROVAL (one reference)
MEPB/MED/25/103/XI/31 7th January, 2025
The Chairman,
Special Committee on Rehabilitation of Public Schools
16, Ogundana Street, Off Allen Avenue,
Ikeja,
Lagos.
PRE-PAYMENT CERTIFICATION:
RENOVATION OF 17+1 CLASSROOM BLOCK A AND ADMIN BLOCK AT COMMUNITY SENIOR GRAMMAR SCHOOL, IPAJA, AYOBO LCDA, ALIMOSHO & RENOVATION OF 6 CLASSROOM BLOCK AT AFRICAN CHURCH PRIMARY SCHOOLS 2, MEIRAN & RENOVATION OF 6 CLASSROOM BLOCK AT UNITY SENIOR COLLEGE, OKE-ODO, LAGOS
I am directed to refer to your letter Ref. No. SCRPS/W/NS/006/2023/136 dated 12th March, 2025 respectively, on the above subject and inform you that approval for the Pre-payment Certificates has been granted in the following sums:
S/N | Contractor | Amount | Remarks
1 | Messrs. Aston Constructions Limited | 6072240.6145 | Retention Payment
2 | Messrs. Kinghorse International Limited | 1682413.171 | Retention Payment
3 | Messrs. Andall Project Limited | 13544043.7966 | Final Payment
2. The Original Inspection Report and Pre-Payment Certificate are attached for your information and further necessary actions, please.
3. Thank you.
Alawiye, K.T. (Ms.)
For: The Permanent Secretary